## Practical_Gantt Chart_updated
| HSV2 Product Development |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan
|  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Subsystem : PCB Design and Fabrication | bar: Aug W4 to Oct W1; Nov W1 to Dec W2
| 1.1 | Module 1 : Requirement Analysis & Customer Approval | bar: Aug W4
|  | 1.1.1 | Initial Stakeholders meeting
|  | 1.1.2 | Defining Project Scope and Objectives
|  | 1.1.3 | Collecting customer requirements and compliances
|  | 1.1.4 | Review and validate the customer requirements
|  | 1.1.5 | Obtain formal customer approval
| 1.2 | Module 2 : Components Selection | bar: Aug W4 to Sep W1
|  | 1.2.1 | Define the functions and specifications of the product
|  | 1.2.2 | Component exploration – Justification and working principle of each component
|  | 1.2.3 | Datasheet Study – Analyze electrical characteristics, packaging, pinout, etc
|  | 1.2.4 | Identify the Passive Components Resistors, capacitors, inductors: values & tolerance.
|  | 1.2.5 | Architecture Diagram – Block-level system overview with functional mapping
|  | 1.2.6 | Finilze the Functional Components V1
| 1.3 | Module 3 : Schematic designing, Review & Updation | bar: Aug W4 to Sep W2
|  | 1.3.1 | Schematic Symbol Identification and Creation – For custom ICs and uncommon parts
|  | 1.3.2 | Footprint Identification and Creation – Based on physical part dimension & pad size
|  | 1.3.3 | Schematic Connection – Wire signals, power, ground, I/O, etc
|  | 1.3.3.1 | Define and Test Electrical Rule Check (ERC) – Net warnings, unconnected pins, etc
|  | 1.3.4 | Layout Segregation – Group analog, digital, power sections
|  | 1.3.5 | Generate Netlist
|  | 1.3.6 | Schematic Prototype 1 – Simulation and Verification – Simulate circuit behavior(ERC)
|  | 1.3.7 | Schematic Iteration – Modify based on simulation or peer review
|  | 1.3.7.1 | Optimizing high-speed PCB schematic
|  | 1.3.7.2 | Placing the components efficiently
|  | 1.3.8 | Schematic Version 2 – Simulation and Verification – Final simulation to validate logic
| 1.4 | Module 4 : Components Purchase | bar: Sep W3 to Oct W3
|  | 1.4.1 | Procurement of Functional Components for Prototype 1
|  | 1.4.2 | Iteration 2 Components Procurement
| 1.5 | Module 5 : PCB Layout Designing | bar: Sep W3 to Oct W2
|  | 1.5.1 | Define the board stack-up
|  | 1.5.2 | Placing components in the layout editor
|  | 1.5.3 | Routing : Connection between the components
|  | 1.5.4 | Define the zone area
|  | 1.5.5 | Set up length-matching rules
|  | 1.5.6 | length tuning
|  | 1.5.7 | Defining custom design rules
|  | 1.5.8 | Custom rules are set for differential pairs
|  | 1.5.9 | Assign violation severity
|  | 1.5.10 | Design rule check report
|  | 1.5.11 | Rectifying DRC Errors
| 1.6 | Module 6 : PCB Manufacturing | bar: Oct W3 to Oct W5
|  | 1.6.1 | Gerber File Generation – Output for top, bottom, drill, mask, silk, Componernt placement Position
|  | 1.6.2 | Verify the production files using the Gerber Viewer
|  | 1.6.3 | PCB Milling – CNC milling
|  | 1.6.4 | Continuity Check in Physical Board – Verify all traces (Actuals thicknesses) and vias for open/shorts
|  | 1.6.5 | Layer-to-layer registration
| 1.7 | Module 7 : PCB Assembly | bar: Nov W1
Assembly – Mount and solder components reflow
| 1.8 | Module 8 : Board Bring up testing | bar: Nov W2
|  | 1.8.1 | Power-On Self Check – Confirm power rails, voltage regulators, and no smoke
|  | 1.8.2 | Functional Testing – Test all I/O, communication interfaces, sensors, etc
|  | 1.8.3 | Firmware Upload & Debug – Flash MCU, test logic, and serial debug
|  | 1.8.4 | Performance Benchmarking – Speed, timing, response accuracy, thermal testing
|  | 1.8.5 | Stress Testing – Run under load, voltage, and temperature variations
| 1.9 | Module 9 : Functional Testing and Validation | bar: Nov W3 to Dec W1
| 1.1 | Module 10 : Documentation | bar: Dec W2
2 | Subsystem : (Industry Design Mechanical Design) IDMD | bar: Aug W1 to Dec W4
| 2.1 | Module 1 : Concept Development |  | Aug W3: Concept 2; Nov W2: DFMA
|  | 2.1.1 | User Need Analysus
|  | 2.1.2 | Functional Requirement
|  | 2.1.3 | Initial Concept Model
| 2.2 | Module 2 : Design & Prototyping |  | Sep W3: Prototype 2; Nov W3: Prototype 3
|  | 2.2.1 | 3D Modeling & Ergonomics
|  | 2.2.2 | Low-Fidelity Prototyping
| 2.3 | Module 3 : Electronics Integration | bar: Nov W1; Dec W2
|  | 2.3.1 | Hardware Integration
|  | 2.3.2 | Mechanical Design Refinement
|  | 2.3.3 | Functional Prototype - External Agencies for 3D printing
| 2.4 | Module 4 : Pilot-Production & Manufacturing |  | Nov W2: External
|  | 2.4.1 | Identifying vendors for production
|  | 2.4.2 | DFM - Injection mold design
|  | 2.4.3 | Finalized Design and Production
|  | 2.4.4 | Assembly and Test
3 | Subsystem : Embedded Board Support Package Development | bar: Aug W4 to Oct W1; Nov W1 to Nov W3
| 3.1 | Module 1: Platform Bring-up & Kernel Boot on QCS6490 | bar: Aug W3 to Aug W4
| 3.2 | Module 2: Camera Driver Integration (IMX577 & OV9281) | bar: Sep W1 to Sep W2
| 3.3 | Module 3 : Audio Interface Enablement (Speaker + Microphone) | bar: Sep W2 to Sep W3
| 3.4 | Module 4 : Sensor Integration (IMU, Battery, Proximity) | bar: Sep W3 to Sep W4
| 3.5 | Module 5 : GPIO Button Handling | bar: Sep W4
| 3.6 | Module 6 : Connectivity Stack Enablement | bar: Sep W4 to Oct W1
| 3.7 | Module 7 : Python Env + AI Libraries Integration | bar: Oct W2
| 3.8 | Module 8 : System Testing & Optimization | bar: Oct W3
| 3.9 | Module 9 : Documentation & Knowledge Transfer | bar: Oct W4
4 | Subsystem : AI/ML Algorithm | bar: Aug W4 to Jan W1
| 4.1 | Unified YOLO custom model creation | bar: Aug W4 to Oct W5
|  | 4.1.1 | Dataset Curation - Collect indoor/outdoor images and videos with Obstacles/Objects/Landmarks/Signboards/Currency/Animals/People/Faces | bar: Aug W4 to Sep W2
|  | 4.1.2 | Annotation of Obstacles & Objects - Draw bounding boxes and assign class labels(with segmentation) External partnership (Ex: haidata.ai) | bar: Sep W2 to Oct W1
|  | 4.1.3 | Model Training - Train the Unified YOLO model on curated dataset | bar: Oct W1 to Oct W2
|  | 4.1.4 | Model Evaluation - Evaluate mAP, precision, recall on test set | bar: Oct W3
|  | 4.1.5 | Hyperparameter Tuning - Improve performance via learning rate, batch size tuning | bar: Oct W4
|  | 4.1.6 | Deployment Testing - Test model on target device for latency, accuracy | bar: Oct W4 to Oct W5
| 4.2 | Optimisation of Base YOLO Model on QCS6490 | bar: Aug W4 to Sep W3
|  | 4.2.1 | Model Selection and conversion (Quantisation if needed) - Choose a base YOLO model (e.g., YOLOv5s or YOLOv8n), Convert base model to ONNX or TFLite for Qualcomm | bar: Aug W4
|  | 4.2.2 | Installalation - Install QCS6490 SDKs and Tools | bar: Sep W1 to Sep W2
|  | 4.2.3 | Inferencing - Implement Inference Pipeline on GPU or NPU | bar: Sep W2 to Sep W3
| 4.3 | Obstacle Avoidance & 3D Environment Awareness | bar: Sep W1 to Nov W3
|  | 4.3.1 | Setting up a Custom camera calibration | bar: Sep W1 to Sep W4
|  | 4.3.2 | VSLAM Implementation for 3D Mapping | bar: Sep W4 to Oct W2
|  | 4.3.3 | Object Detection overlay on 3D Map | bar: Oct W2 to Oct W3
|  | 4.3.4 | 3D Obstacle Detection + Object Identification | bar: Oct W3 to Oct W4
|  | 4.3.5 | Direction, Distance Detection | bar: Oct W5
|  | 4.3.6 | Voice over cues for obstacle avoidance | bar: Nov W1 to Nov W2
|  | 4.3.7 | Logic for Obstacle in the walk path, region of interest (next few steps), hanging from above | bar: Nov W2 to Nov W3
| 4.4 | Turn by Turn Navigation | bar: Sep W3 to Oct W5
|  | 4.4.1 | Implementation of offline map and routing algorithm using map providers sdk | bar: Sep W3
|  | 4.4.2 | Source selection using GPS and Destination selection using voice over and saved addresses | bar: Sep W4 to Oct W1
|  | 4.4.3 | Voice over of entire journey | bar: Oct W2
|  | 4.4.4 | Overlay of SLAM + Segmentation on top of map | bar: Oct W1 to Oct W2
|  | 4.4.5 | Fuse map’s turn guidance and obstacle guidance over voice | bar: Oct W3
|  | 4.4.6 | Pedestrian Path identification, Potholes, ramps, slopes, lamp posts, Walk path benches, walk path barriers | bar: Oct W3
|  | 4.4.7 | Safe path assisstance Ex: Walk on the platform, Avoid walking on the center of the road | bar: Oct W4
|  | 4.4.8 | NLP Engine for Input and output text processing | bar: Oct W4 to Oct W5
| 4.5 | Landmark Recognition & Misplaced Object Locating | bar: Oct W2 to Nov W2
|  | 4.5.1 | 3D Object Detection using SLAM + YOLO | bar: Oct W2 to Oct W3
|  | 4.5.2 | Distance and Direction Estimation, find the Surface | bar: Oct W4
|  | 4.5.3 | Logic to convert into Audio cues: Ex: Cell phone, 5 ft ahead, at 11'o clock on the table | bar: Oct W5
|  | 4.5.4 | Play Spatial Audio in the object location for assisting VI move toward the obstacle | bar: Oct W5
|  | 4.5.5 | Memory logic to remember and find user requested object | bar: Nov W1
|  | 4.5.6 | Handtracking for inhand object detection | bar: Nov W2
| 4.6 | Dynamic Face Recognition | bar: Aug W4 to Oct W1
|  | 4.6.1 | Pipeline for processing faces from the YOLO object detection pipeline | bar: Aug W4
|  | 4.6.2 | FaceNet Model Optimization - Perform Conversion(ONNX), Quantization(INT8/F16) for Qualcomm Accelerated Inferencing | bar: Sep W1 to Sep W2
|  | 4.6.3 | Sync logic new faces from Mobile and Spectacle | bar: Sep W3
|  | 4.6.4 | Logic for Detecting closest 3 faces during navigation and telling their names | bar: Sep W4 to Oct W1
|  | 4.6.5 | Push to talk logic for name all the faces in the room | bar: Oct W1
|  | 4.6.6 | Turn off Face Detection logic | bar: Oct W1
| 4.7 | Signboard Recognition | bar: Oct W2 to Oct W5
|  | 4.7.1 | YOLO Inference Integration- Test custom trained YOLO model to detect signboards | bar: Oct W2 to Oct W3
|  | 4.7.2 | Evaluate OCR - Test OCR tools (e.g., PaddleOCR, EasyOCR, TesseractOCR) for speed, accuracy, and computational efficiency for deployment on QCS6490. | bar: Oct W4
|  | 4.7.3 | Testing & Optimization - Evaluate pipeline performance (latency, accuracy) on Qualcomm board | bar: Oct W5
| 4.8 | Currency Recognition | bar: Nov W1 to Nov W3
|  | 4.8.1 | YOLO Inference Integration - Test custom trained YOLO model to detect currency notes(₹10, ₹20, ₹50, ₹100, ₹200, ₹500) | bar: Nov W1
|  | 4.8.2 | OCR - Integrate OCR to validate denomination and Extracting Text From the menu. | bar: Nov W2
|  | 4.8.3 | Testing & Optimization - Evaluate pipeline performance (latency, accuracy) on Qualcomm board | bar: Nov W3
| 4.9 | Book Reading System & Menucard reading | bar: Nov W1 to Dec W1
|  | 4.9.1 | Turn on Book reading mode, Identify Turn page, Capture and flatten current page for easy interpertation | bar: Nov W1
|  | 4.9.2 | OCR for Page Text - Integrate OCR for extracting text from the page. | bar: Nov W2
|  | 4.9.3 | VLM Evaluation & Benchmark - Evaluate VLMs (e.g., SmolVLM) on accuracy, latency, and compatibility with QCS6490. | bar: Nov W3 to Nov W4
|  | 4.9.4 | VLM Integration- Integrate VLM for summarization and open ended queries(eg; what is the title of the book?) | bar: Nov W4 to Dec W1
|  | 4.9.5 | Testing & Optimization - Evaluate pipeline performance (latency, accuracy) on Qualcomm board | bar: Dec W1
| 4.1 | Text to Speech and Speech to Text Module | bar: Sep W4 to Oct W5
|  | 4.10.1 | Optimised TTS and STT Model Deployment | bar: Sep W4 to Oct W1
|  | 4.10.2 | Custom Text to Speech pipeline based on prioritization (Obstacle, Map Navigation, Face Recognition) | bar: Oct W2 to Oct W3
|  | 4.10.3 | Precomputed word for faster voice generation | bar: Oct W3
|  | 4.10.4 | Speech to text pipeline and function mapping logic | bar: Oct W3 to Oct W4
|  | 4.10.5 | Testing & Optimization - Evaluate pipeline performance (latency, accuracy) on Qualcomm board | bar: Oct W4 to Oct W5
| 4.11 | UPI Payment Logic | bar: Nov W1 to Dec W2
|  | 4.11.1 | Detect UPI QR using YOLO | bar: Nov W1
|  | 4.11.2 | Pass it to Mobile App | bar: Nov W2
|  | 4.11.3 | Trigger payment action from Mobile App | bar: Nov W2 to Nov W3
|  | 4.11.4 | Voice over for QR detection and payment triggering | bar: Nov W4 to Dec W1
|  | 4.11.5 | Testing & Optimization - Evaluate pipeline performance (latency, accuracy) on Qualcomm board | bar: Dec W1 to Dec W2
| 4.12 | Scene Understanding and Q&A Features | bar: Oct W5 to Nov W4
|  | 4.12.1 | Optimising VLM for Edge Inferencing | bar: Oct W5 to Nov W1
|  | 4.12.2 | Scene Description Pipeline Implementation | bar: Nov W1
|  | 4.12.3 | Push-to-Talk Q&A System Integration | bar: Nov W2
|  | 4.12.4 | Evaluation of VLM for Common scenarios | bar: Nov W3 to Nov W4
| 4.13 | Power Optimisation | bar: Nov W4 to Dec W2
|  | 4.13.1 | Turn off Face Recognition to increase battery | bar: Nov W4
|  | 4.13.2 | Turn off GPS during indoor navigation | bar: Dec W1
|  | 4.13.3 | Turn off SLAM processing when stationary for extended periods | bar: Dec W2
|  | 4.13.4 | Reduce camera frame rate during idle mode | bar: Dec W2
| 4.14 | Perfomance Optimisation | bar: Nov W2 to Nov W3; Dec W2 to Jan W1
|  | 4.14.1 | Implement multi-threading for parallel AI model execution | bar: Nov W2 to Nov W3; Dec W2 to Dec W3
|  | 4.14.2 | Use hardware-accelerated image preprocessing (resize, normalize, format conversion) | bar: Nov W2 to Nov W3; Dec W2 to Dec W3
|  | 4.14.3 | Optimize audio processing pipeline for real-time TTS and spatial audio | bar: Dec W4
|  | 4.14.4 | Optimize data transfer between CPU, GPU, NPU, and DSP | bar: Dec W4 to Jan W1
|  | 4.14.5 | Implement intelligent caching for frequent operations | bar: Dec W4 to Jan W1
| 4.15 | Comprehensive Testing | bar: Nov W2 to Nov W3; Dec W2 to Jan W1
|  | 4.15.1 | Field testing with visually impaired users | bar: Nov W2 to Nov W3; Dec W2 to Jan W1
|  | 4.15.2 | Performance benchmarking across environments | bar: Nov W2 to Nov W3; Dec W2 to Jan W1
|  | 4.15.3 | Integration testing | bar: Nov W2 to Nov W3; Dec W2 to Jan W1
| 4.16 | Data Annotation |  | Sep W1: External -HiData
5 | Subsystem : Android App | bar: Sep W3 to Sep W4; Oct W4 to Oct W5; Nov W3 to Nov W4; Dec W3 to Jan W4
| 5.1 | Andorid App | bar: Sep W3 to Sep W4; Oct W4 to Oct W5; Nov W3 to Nov W4; Dec W3 to Jan W4
|  | 5.1.1 | User Onboarding | bar: Sep W3
|  | 5.1.2 | Device Configuration | bar: Sep W3 to Sep W4
|  | 5.1.3 | Face capture, Tag name and sync with spectacle | bar: Oct W4 to Oct W5
|  | 5.1.4 | Trigget UPI payments from QR Code Image from Spectacle | bar: Nov W3 to Nov W4
|  | 5.1.5 | Backend Integeration | bar: Nov W4
|  | 5.1.6 | Testing & Optimization - Evaluate pipeline performance (latency, accuracy) on Qualcomm board | bar: Oct W4 to Oct W5; Dec W3 to Jan W4
6 | Subsystem: Platform Enablement & BSP Dependencies (to be procured via Lantronix/Qualcomm) | bar: Aug W4 to Dec W4
| 6.1 | QCS6490 BSP Source Access
|  | 6.1.1 | Linux Kernel Source & Board Support Package
|  | 6.1.2 | Device Tree Blobs/Overlays (all peripherals: camera, IMU, etc.)
|  | 6.1.3 | Kernel Patches for camera, display, and audio integration
|  | 6.1.4 | Root Filesystem & Build Metadata
| 6.2 | Proprietary Toolchains & SDKs
|  | 6.2.1 | Hexagon DSP Toolchain (AI/ML offload & DSP firmware)
|  | 6.2.2 | AI Engine Compiler, Python Interface Support
|  | 6.2.3 | Camera ISP Stack, Tuning tool (Chromatix/ISP)
|  | 6.2.4 | Qualcomm Connectivity Stack SDK (WiFi/BT)
|  | 6.2.5 | Secure Boot & Firmware Signing utilities
| 6.3 | Reference Designs & Schematics
|  | 6.3.1 | Reference Carrier Board (CCB) Design files
|  | 6.3.2 | Hardware Interface Documentation (JTAG, UFS, etc.)
| 6.4 | Technical Documentation & Support
|  | 6.4.1 | Qualcomm Dev Portal/License/FAE Access
|  | 6.4.2 | System Bring-up and Debugging Guidelines
|  | 6.4.3 | Access to Middleware/Platform Integration Guides
| 6.5 | Supply Chain & SCM Support
|  | 6.5.1 | SOM/Dev Kit Procurement via Preferred Vendor
|  | 6.5.2 | Priority Support for Firmware/Module Issues
7 | Subsystem: Data Annotation | bar: Sep W1 to Oct W2
| 7.1 | Dataset Creation & Organization
|  | 7.1.1 | Curate raw data (images and video) covering required environments (indoor, outdoor, transit, home, commercial, education, etc.)
|  | 7.1.2 | Organize data by category, scenario, and use case for efficient annotation and model training
| 7.2 | Annotation Preparation & Tuning
|  | 7.2.1 | Define comprehensive annotation guidelines for all required categories and classes
|  | 7.2.2 | Define comprehensive annotation guidelines for all required categories and classes
|  | 7.2.3 | Balance dataset for class representation (static, dynamic, rare events/objects)
| 7.3 | Bounding Box Annotation
|  | 7.3.1 | Static obstacles: furniture, infrastructure, public transport objects (bus stops, benches, etc.)
|  | 7.3.2 | Dynamic obstacles: annotating people, vehicles, animals in real and simulated environments
|  | 7.3.3 | Indoor landmarks: elevators, escalators, restrooms, office/store entrances, commercial spaces
|  | 7.3.4 | Outdoor landmarks: bus stands, metro/rail stations, crosswalks, signage, ATMs, help-desks
|  | 7.3.5 | Specialized objects: currency notes, signboards, menu cards, price tags, ID cards
| 7.4 | Semantic Segmentation Annotation
|  | 7.4.1 | Navigation surfaces: roads, platforms, walkways, pedestrian paths (separate class masks)
|  | 7.4.2 | Hazard zones: stagnant water, garbage, potholes, slippery/uneven surfaces, construction
|  | 7.4.3 | Environmental elements: buildings, trees, sky, ground, fences, surface type classification
|  | 7.4.4 | Indoor navigation: floor types (tiles, carpet, wood), corridors, staircases, elevators, obstacles, and vertical elements (partitions, columns)
| 7.5 | Quality Review & Dataset Integration
|  | 7.5.1 | Validation of annotation accuracy (manual review, spot checks, class distribution analysis)
|  | 7.5.2 | Dataset packaging for model training (export in standard formats: COCO, Pascal VOC, etc.)
|  | 7.5.3 | Versioning and change tracking for evolving datasets
8 | Subsystem: Mould /Tool Making | bar: Sep W3 to Nov W4
| 9.1 | Partner Engagement ,DFM Review & Optimisation | bar: Sep W3 to Sep W4
|  | 9.1.1 | Review part design for manufacturability and injection moulding
|  | 9.1.2 | Finalize part design and get customer approval
| 9.2 | Mould Design | bar: Sep W4 to Oct W3
|  | 9.2.1 | Tool design (core/cavity, runners, cooling, ejection)
|  | 9.2.2 | Mould-flow simulation and DFM sign-off
| 9.3 | Tool Fabrication & Machining | bar: Oct W3 to Nov W1
|  | 9.3.1 | Procure steel and create tool/core/cavity via CNC machining
|  | 9.3.2 | Tool assembly, bench trial and fit-up inspection
|  | 9.3.3 | Initial trial in bench press for movement check
| 9.4 | First Tool Trial & Tuning (T0/T1) | bar: Oct W5 to Nov W1
|  | 9.4.1 | Moulding T0 samples, initial inspection
|  | 9.4.2 | Debug and optimize tool (rework, venting, cooling update, etc)
|  | 9.4.3 | Repeat trial (T1/T2 as needed), measure dimensional accuracy
| 9.5 | Part Validation & Approval | bar: Nov W1 to Nov W2
|  | 9.5.1 | Functional and cosmetic inspection (fit, finish, color)
|  | 9.5.2 | Material/color matching & approval
|  | 9.5.3 | Tool sign-off (customer approval)
| 9.6 | Pilot Production (Pre-production Batch) | bar: Nov W2 to Nov W3
|  | 9.6.1 | Run pilot batch using production settings
|  | 9.6.2 | QA and assembly trial with PCB/hardware
| 9.7 | Tooling Documentation & Handover | bar: Nov W3
|  | 9.7.1 | Transfer of drawings, tool maintenance docs, warranty info
| 9.8 | Mass Production Handover | bar: Nov W4
|  | 9.8.1 | Mould/tool handed over to supplier for production
9 | Subsystem: EMS (Electronics Manufacturing Service) – 500 Unit Production | bar: Nov W1 to Jan W1
| 10.1 | EMS Partner Engagement & Preparation | bar: Nov W1 to Nov W2
|  | 10.1.1 | EMS Selection (RFP/RFQ, Due Diligence, NDA)
|  | 10.1.2 | NPI (New Product Introduction) kickoff: Share documentation, BoM, Gerbers, Assembly drawings.
|  | 10.1.3 | Process walk-through: DFM/DFA review, tooling handover, fixture requirement definition.
|  | 10.1.4 | Finalize Work Orders, supply terms, part sourcing policy (consignment/turnkey/hybrid)
| 10.2 | Material Procurement & SMT Preparation | bar: Nov W2 to Dec W2
|  | 10.2.1 | Long Lead Material (LLI) ordering (SoM, Sensors, Connectors)
|  | 10.2.2 | Regular & passive part procurement (Resistors, capacitors, ICs, connectors)
|  | 10.2.3 | Mechanical parts & plastics procurement (using finalized injection-moulded tools)
|  | 10.2.4 | Incoming Material Inspection (fit, finish, compliance)
| 10.3 | PCB Assembly (Pilot & Volume) | bar: Dec W1 to Dec W2
|  | 10.3.1 | SMT Line Programming & Stencil Fabrication
|  | 10.3.2 | Pilot Batch Run (15–20 units for process validation)
|  | 10.3.3 | SMT/through-hole population, reflow/wave soldering
|  | 10.3.4 | AOI/Visual inspection & rework (pilot)
|  | 10.3.5 | Process Feedback Loop (DFM changes, if any)
| 10.4 | System Integration & Mechanical Assembly | bar: Dec W2
|  | 10.4.1 | Receive and QC all plastics/enclosures from tool maker/moulder
|  | 10.4.2 | Sub-assembly build: PCBA + enclosure, battery, connectors
|  | 10.4.3 | Integration of battery, magnetic charging, speakers, microphones, optical assemblies
|  | 10.4.4 | Mechanical fastener & fit checks, mark any tolerance issues for DFM
| 10.5 | Functional Testing & Pre-Compliance | bar: Dec W3
|  | 10.5.1 | In-circuit Test (ICT) at bare-board stage (before assembly)
|  | 10.5.2 | Flash programming, firmware load, hardware bring-up
|  | 10.5.3 | Full Functional Testing – camera, audio, sensors, wireless, battery
|  | 10.5.4 | Pre-compliance (EMI/ESD, battery charging, regulatory bonds)
|  | 10.5.5 | Test record cataloging (serialization)
| 10.6 | Final Assembly, QA | bar: Dec W4
|  | 10.6.1 | Run Rate Production (up to 500 units) with inline QA
|  | 10.6.2 | Cosmetic inspection & cleaning
|  | 10.6.3 | Out-of-box audit (OBA), field simulation
|  | 10.6.4 | Burn-in testing (e.g., 12–24h runtime per batch/lot)
|  | 10.6.5 | Safety/label marking, documentation
| 10.7 | Packaging & Dispatch | bar: Jan W1
|  | 10.7.1 | Custom packaging assembly (wearable + magnetic case + chargers + docs)
|  | 10.7.2 | Shipper box build (as per contract/logistics agreement)
|  | 10.7.3 | Shipping logistics (schedule for regional lots if required)
|  | 10.7.4 | “Golden sample” lot storage, warranty spares boxed
| 10.8 | Documentation, Handover & Support | bar: Jan W1
|  | 10.8.1 | Final Production Summary, openness of NPI/FAI (First Article) documents
|  | 10.8.2 | Batch-wise QA records, yield, outgoing and issue log, traceability matrix
|  | 10.8.3 | Production signoff – warranty handover, field support escalation procedure
|  | 10.8.4 | Inventory of production tools, test jigs, leftover materials
10 | Subsystem:Technical Architecture, Overall Design and BoM, Project Management
11 | Subsystem:User Testing | bar: Dec W1 to Dec W4

## SubSystems (hidden)
Hearsight -V2 Product Sub system definition |  |  |  | Duration Days |  | Named Resources | Progress | Supporting Documents | External Expect Intervention
1 | Subsystem : PCB Design and Fabrication
| 1.1 | Module 1 : System Planning & Component Selection |  | 3 Weeks (1W R&D + 2W Task) | 15
|  | 1.1.1 | Task 1: Architecture Diagram – Block-level system overview with functional mapping | 3 Weeks (1W R&D + 2W Task) |  |  | 90% | Link
|  | 1.1.2 | Task 2: Component exploration – Justification and working principle of each component |  |  |  |  | -
|  | 1.1.3 | Task 3: Datasheet Study – Analyze electrical characteristics, packaging, pinout, etc |  |  |  | 40 % | Hs doubts
|  | 1.1.4 | Task 4: Component Finalization
|  | 1.1.5 | Task 5: Identify the Passive Components Resistors, capacitors, inductors: values & tolerance.
| 1.2 | Module 2 : Schematic Design |  | 2 Weeks | 10
|  | 1.2.1 | Task 6: Schematic Symbol Identification or Creation – For custom ICs and uncommon parts | 2 Weeks
|  | 1.2.2 | Task 7 : Footprint Identification or Creation – Based on physical part dimension & pad size
|  | 1.2.3 | Task 8 : Schematic Connection – Wire signals, power, ground, I/O, etc
|  | 1.2.4 | Task 9 : Layout Segregation – Group analog, digital, power sections for better routing
|  | 1.2.5 | Task 10: Define and Test Electrical Rule Check (ERC) – Net warnings, unconnected pins, etc
|  | 1.2.6 | Task 11: Schematic Version 1 – Simulation and Verification – Simulate circuit behavior(ERC) | [5 empty] | Expert Validation Required
|  | 1.2.7 | Task 12: Schematic Iteration – Modify based on simulation or peer review
|  | 1.2.8 | Task 13: Schematic Version 2 – Simulation and Verification – Final simulation to validate logic | [5 empty] | Expert Validation Required
| 1.3 | Module 3 : PCB Layout Design |  | 2 Weeks | 10
|  | 1.3.1 | Task 14: Routing Version 1 – Initial routing of all signals & power nets | 2 Weeks
|  | 1.3.2 | Task 15: Define and Test Design Rule Check (DRC) Definition & Testing – Set trace width, clearance, via sizes
|  | 1.3.3 | Task 16: Power Integrity and Signal Integrity Checks – Ensure stable voltage and noise-free lines | [5 empty] | Expert Validation Required
|  | 1.3.4 | Task 17: PCB Layout Validation and Iteration
| 1.4 | Module 4 : Fabrication & Assembly |  | To Be Estimated(Outsourcing)
|  | 1.4.1 | Task 17: Gerber File Generation – Output for top, bottom, drill, mask, silk, etc | To Be Estimated(Outsourcing)
|  | 1.4.2 | Task 18: PCB Milling – CNC milling or order from PCB manufacturer
|  | 1.4.3 | Task 19: Continuity Check in Physical Board – Verify all traces and vias for open/shorts
|  | 1.4.4 | Task 20: Task Assembly – Mount and solder components (manual or reflow)
| 1.5 | Module 5 : Board Bringup & Functional Testing |  | 2 Weeks | 10
|  | 1.5.1 | Task 21 : Power-On Self Check – Confirm power rails, voltage regulators, and no smoke | 2 Weeks
|  | 1.5.2 | Task 22 : Functional Testing – Test all I/O, communication interfaces, sensors, etc
|  | 1.5.3 | Task 23 : Firmware Upload & Debug – Flash MCU, test logic, and serial debug
|  | 1.5.4 | Task 24 : Performance Benchmarking – Speed, timing, response accuracy, thermal testing | [5 empty] | Expert Validation Required
|  | 1.5.5 | Task 25 : Stress Testing – Run under load, voltage, and temperature variations
| 1.6 | Module 6 : Testing & Compliance |  | To Be Estimated(Outsourcing)
|  | 1.6.1 | Task 26 : Signal Quality Validation – Use oscilloscope to validate rise/fall times, reflections | To Be Estimated(Outsourcing)
|  | 1.6.2 | Task 27 : EMI/EMC Pre-Compliance Testing – Test for noise, radiation (if applicable)
|  | 1.6.3 | Task 28 : Thermal Analysis – IR camera or thermocouples to spot hot areas
|  | 1.6.4 | Task 29 : Grounding & Isolation Verification – Validate safety practices in mixed-signal or high-voltage circuits
|  | 1.6.5 | Task 30 : Design Validation Review (DVR) – Cross-check against requirements before deployment
|  | 1.6.6 | Task 31 : Final QA Documentation – Include test reports, design files, BoM, and review logs
2 | Subsystem : (Industry Design Mechanical Design) IDMD
| 2.1 | Module 1 : Concept Development |  | 1 Week | 5
|  | 2.1.1 | User Need Analysus | 1 Week
|  | 2.1.2 | Functional Requirement
|  | 2.1.3 | Initial Concept Model
| 2.2 | Module 2 : Design & Prototyping |  | 3 Weeks | 15
|  | 2.2.1 | 3D Modeling & Ergonomics | 3 Weeks
|  | 2.2.2 | Low-Fidelity Prototyping
| 2.3 | Module 3 : Electronics Integration |  | 3 Weeks | 15
|  | 2.3.1 | Hardware Integration | 3 Weeks
|  | 2.3.2 | Mechanical Design Refinement
|  | 2.3.3 | Functional Prototype - External Agencies for 3D printing
| 2.4 | Module 4 : Pre-Production & Manufacturing |  | To Be Estimated(Outsourcing)
|  | 2.4.1 | Finalized Design | To Be Estimated(Outsourcing)
|  | 2.4.2 | DFM - Injection mold design
|  | 2.4.3 | Identifying vendors for production
3 | Subsystem : Embedded Board Support Package Development |  |  |  |  | Selva J, Nandalal Parthiban, Dhayalan R,Jeejy t,
| 3.1 | Module 1: Platform Definition & Hardware Abstraction |  | 4 Weeks (1W - Tool Setup, 2W - L&D, 1W - Implementation)
|  | 3.1.1 | Platform Architecture Definition - Define SoC blocks, memory map, boot flow, power rails | 4 Weeks (1W - Tool Setup, 2W - L&D, 1W - Implementation)
|  | 3.1.2 | Bootloader Selection & Configuration - Setup U-Boot/Barebox, enable storage & peripheral init
|  | 3.1.3 | Device Tree Setup (DTS/DTB) - Map hardware in DTS: CPU, buses, memory, GPIO
|  | 3.1.4 | Linux Kernel Configuration & Patching - Enable drivers, add defconfig options, apply patches | [5 empty] | Expert Guidance Required
|  | 3.1.5 | Filesystem Selection & Preparation - Choose and build BusyBox, Yocto, Debian rootfs
| 3.2 | Module 2: Camera Subsystem Integration (Mono & RGB) |  | 2 weeks
|  | 3.2.1 | Camera Interface Definition - Define CSI/LVDS/USB setup, voltage rails, and pinmux | 2 weeks
|  | 3.2.2 | Driver Integration - Add or enable V4L2 drivers for mono/RGB sensors | [5 empty] | Expert Guidance Required
|  | 3.2.3 | Image Format & Frame Rate Handling - Validate pixel format, resolution, FPS using v4l2-ctl
|  | 3.2.4 | Streaming & Image Pipeline Testing - Stream via GStreamer/FFmpeg, validate pipeline
|  | 3.2.5 | Performance Optimization - DMA tuning, frame drops, image latency checks
| 3.3 | Module 3 : Audio Subsystem Development (Mic & Speaker) |  | 1 week
|  | 3.3.1 | Codec/Driver Setup - Integrate ALSA drivers for mic/speaker, I2S or USB | 1 week
|  | 3.3.2 | Audio Path Configuration - Configure mixer, gain, audio routing in DTS
|  | 3.3.3 | Audio Playback and Capture Testing - Use arecord, aplay, alsamixer for validation
|  | 3.3.4 | Latency, Echo & Quality Testing - Test for delay, echo, AEC; full-duplex streaming
| 3.4 | Module 4 : IO Peripheral Integration |  | 1 week
|  | 3.4.1 | IO Pinmux & Device Tree Configuration - Map GPIO, I2C, SPI, UART, ADC, PWM in DTS | 1 week
|  | 3.4.2 | Peripheral Bus Testing - Test I2C/SPI/UART using external devices/loopbacks
|  | 3.4.3 | GPIO & Interrupt Testing - Toggle inputs/outputs, handle edge interrupts
|  | 3.4.4 | Analog & PWM Channel Bring-Up - Validate ADC linearity and PWM frequency/duty
| 3.5 | Module 5 : BSP Build System & Automation |  | 3 weeks
|  | 3.5.1 | Build System Setup (Yocto/Buildroot/Manual) - Manage bootloader, kernel, rootfs builds | 3 weeks |  |  |  |  | Expert Guidance Required
|  | 3.5.2 | Flashing & Provisioning Automation - Create SD/eMMC flash scripts, device identity setup | [5 empty] | Expert Guidance Required
|  | 3.5.3 | Board Bring-up Checklist & Logs - Standardize logs: boot time, serial console, dmesg | [5 empty] | Expert Guidance Required
4 | Subsystem : AI/ML Algorithm
5 | Subsystem : Android App development and System Integeration
| 5.1 | Android application development
|  | 5.1.1 | Android app development | External
|  | 5.1.2 | API Integeration and testing
|  | 5.1.3 | Error Handling
5